## Status Report
ELEC 4000 Senior Design Status Report Excel Template Created by: David Mason
Project Name: |  | AU Electro-Aviation
Team 1, Members: |  | Jens Johnson, Shaquana Peterson, Ed Budimier, David Mason, Adam Gould
Report Date: |  | 2011-02-23
Project Description: |  | Autonimous aviation with indoor helicopter.
Cycle (P, 1, or 2): |  | Cycle One (1)
Cycle Intent: |  | Begin prototype by designing a front-end application and circuit design capable of being interfaced to an electric, 26" indoor helicopter's existing control board.
TASKS
[8 empty] | Planned |  |  | Actual
Task # | Task Description (Add rows as needed) | [6 empty] | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status (%) Compl.. | Actual hours this cycle | Total Hours
1 | Team Management | [6 empty] | 1 | 7.5 | 30
2 | Reporting | [6 empty] | 1 | 2 | 8
3 | Editing | [6 empty] | 1 | 0.5 | 2
4 | Website Management | [6 empty] | 1 | 1 | 4
5 | Budgeting | [6 empty] | 1 | 1 | 4
6 | Purchasing/Market Research | [6 empty] | 1 | 1 | 4
7 | Programming | [6 empty] | 1 | 2 | 8
8 | Circuit Design | [6 empty] | 1 | 1 | 4
9 | Prototype Testing and Troubleshooting | [6 empty] | 1 | 1 | 4
10 | Meeting | [6 empty] | 1 | 3 | 12
To insert new row right click on this row number and click insert
1Planned Total should equal (# of team members) x (10 hrs. per week) x (Proposal weeks (3) + Cycle 1 weeks (4) + Cycle 2 weeks (5) = 12 weeks).
2Assumes 7.5 hours per week for 12 weeks. Should be mainly team leader(s).
TEAM MEMBER HOURS
Record # of hours each person spent on each task this week, then total by week, cycle, and project.
Name | Task3 | [9 empty] | Total Hours
2/10/11 - 2/16/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle | Project
David Mason | 5 | 3 | 2 | [6 empty] | 1 | 11 | 11 | 11
Ed Budimier |  | 2 | 3 |  |  | 3 |  |  |  | 2 | 10 | 10 | 10
Shaquana Peterson |  | 2 |  |  | 2 | 4 |  |  |  | 2 | 10 | 10 | 10
Jens Johnson |  | 2 | 3 | 2 |  | 2 |  |  |  | 1 | 10 | 10 | 10
Adam Gould |  | 2 | 3 |  |  | 3 |  |  |  | 2 | 10 | 10 | 10
[10 empty] | Total | 51 | 51 | 51
2/17/11 - 2/23/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle | Project
David Mason | 1.5 | [5 empty] | 1 | 1 | 1 | 2 | 6.5 | 17.5 | 17.5
Ed Budimier |  | 1 |  |  |  |  | 1 | 2 |  | 3 | 7 | 17 | 17
Shaquana Peterson | [5 empty] | 3 |  | 1 |  | 4 | 8 | 18 | 18
Jens Johnson |  |  |  | 1 |  |  | 3 |  | 1 | 2 | 7 | 17 | 17
Adam Gould | 1 |  |  | 1 |  |  | 2 |  | 2 |  | 6 | 16 | 16
[10 empty] | Total | 34.5 | 85.5 | 85.5
2/24/11 - 3/2/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle | Project
David Mason | 2.5 | 1 |  |  |  |  | 1.5 |  | 3 | 3 | 11 | 28.5 | 28.5
Ed Budimier |  | 2 |  |  |  |  | 2 | 1 | 2 | 3 | 10 | 27 | 27
Shaquana Peterson | [5 empty] | 4 |  |  |  | 3 | 7 | 25 | 25
Jens Johnson |  | 1 |  | 2 |  |  |  |  | 1 | 3 | 7 | 24 | 24
Adam Gould | [10 empty] | 0 | 16 | 16
[10 empty] | Total | 35 | 120.5 | 120.5
3/3/11 - 3/9/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle | Project
David Mason | [10 empty] | 0 | 28.5 | 28.5
Ed Budimier | [10 empty] | 0 | 27 | 27
Shaquana Peterson | [10 empty] | 0 | 25 | 25
Jens Johnson | [10 empty] | 0 | 24 | 24
Adam Gould | [10 empty] | 0 | 16 | 16
[10 empty] | Total | 0 | 120.5 | 120.5
Accomplishments since last status report:
1) Prototype built using IR Range Finder 2) Programmed ultrasonic range finder to be implemented on the helicopter
Accomplishments must have some deliverable form (e.g., it cannot be stated that “serial interface programming was learned”; rather, data demonstrating those concepts learned must be presented (e.g. a program that successfully sends a character to serial port is demonstrated).
Obstacles encountered since last status report and actions to deal with same:
1) Damaged Helicopters control board.
Risks facing the project and actions to deal with same:
1) Will we be able to use wireless communications? Program Xbee wireless communication system 2) How will we interface a secondary power supply? Two batteries have been purchased.
Team members should review formal risk management concepts and incorporate those here.
Objectives for the next week:
1) Send a wireless sensor reading to another microcontroller 2) Develop and debug logical program flow. 3) Finish Cycle 1 Report
Ideally, this week’s objectives will be next week’s accomplishments. Like accomplishments, these must be concrete and subject to physical demonstration.
Notes:
This week we went to E-Day to demonstrate our prototype. The IR Sensors capabilities have been explored and used to develop the prototype. A single ultrasonic sensor has been programmed; we will use this program as a basis for all the sensors used on the helicopter.

## David
Date | 2011-02-23
Hours per task
Cycle 1 | Hours per week | Team Management | 9
Week 1 | 11 | Reporting | 4
Week 2 | 6.5 | Editing | 2
Week 3 | 11 | Website Management
Week 4 |  | Budgeting
Purchasing/Market Research
|  | Programming | 2.5
|  | Circuit Design | 1
|  | Prototype Testing and Troubleshooting | 4
|  | Meeting | 6
|  | Total Hours | 28.5

## Edward
Date | 2011-02-23
Hours per task
Cycle 1 | Hours per week | Team Management
Week 1 | 10 | Reporting | 5
Week 2 | 7 | Editing | 3
Week 3 | 10 | Website Management
Week 4 |  | Budgeting
|  | Purchasing/Market Research | 3
|  | Programming | 3
|  | Circuit Design | 3
|  | Prototype Testing and Troubleshooting | 2
|  | Meeting | 8
|  | Total Hours | 27

## Shaquana
Date | 2011-02-23
Hours per task
Cycle 1 | Hours per week | Team Management
Week 1 | 10 | Reporting | 2
Week 2 | 8 | Editing
Week 3 | 7 | Website Management
Week 4 |  | Budgeting | 2
|  | Purchasing/Market Research | 11
Programming
|  | Circuit Design | 1
Prototype Testing and Troubleshooting
|  | Meeting | 9
|  | Total Hours | 25

## Jens
Date | 2011-02-23
Hours per task
Cycle 1 | Hours per week | Team Management
Week 1 | 10 | Reporting | 3
Week 2 | 7 | Editing | 3
Week 3 | 7 | Website Management | 5
Week 4 |  | Budgeting
|  | Purchasing/Market Research | 2
|  | Programming | 3
Circuit Design
|  | Prototype Testing and Troubleshooting | 2
|  | Meeting | 6
|  | Total Hours | 24

## Adam
Date | 2011-02-23
Hours per task
Cycle 1 | Hours per week | Team Management | 1
Week 1 | 10 | Reporting | 2
Week 2 | 6 | Editing | 3
Week 3 |  | Website Management | 1
Week 4 |  | Budgeting
|  | Purchasing/Market Research | 3
|  | Programming | 2
Circuit Design
|  | Prototype Testing and Troubleshooting | 2
|  | Meeting | 2
|  | Total Hours | 16