## Status Report
ELEC 4000 Senior Design Status Report Excel Template Created by: David Mason
Project Name: |  | AU Electro-Aviation
Team 1, Members: |  | Jens Johnson, Shaquana Peterson, Ed Budimier, David Mason, Adam Gould
Report Date: |  | 2011-02-23
Project Description: |  | Autonimous aviation with indoor helicopter.
Cycle (P, 1, or 2): |  | Cycle One (1)
Cycle Intent: |  | Begin prototype by designing a front-end application and circuit design capable of being interfaced to an electric, 26" indoor helicopter's existing control board.
TASKS
[8 empty] | Planned |  |  | Actual
Task # | Task Description (Add rows as needed) | [6 empty] | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status (%) Compl.. | Actual hours this cycle | Total Hours
1 | Team Management | [6 empty] | 1 | 7.5 | 30
2 | Reporting | [6 empty] | 1 | 2 | 8
3 | Editing | [6 empty] | 1 | 0.5 | 2
4 | Website Management | [6 empty] | 1 | 1 | 4
5 | Budgeting | [6 empty] | 1 | 1 | 4
6 | Purchasing/Market Research | [6 empty] | 1 | 1 | 4
7 | Programming | [6 empty] | 1 | 2 | 8
8 | Circuit Design | [6 empty] | 1 | 1 | 4
9 | Prototype Testing and Troubleshooting | [6 empty] | 1 | 1 | 4
10 | Meeting | [6 empty] | 1 | 3 | 12
To insert new row right click on this row number and click insert
1Planned Total should equal (# of team members) x (10 hrs. per week) x (Proposal weeks (3) + Cycle 1 weeks (4) + Cycle 2 weeks (5) = 12 weeks).
2Assumes 7.5 hours per week for 12 weeks. Should be mainly team leader(s).
TEAM MEMBER HOURS
Record # of hours each person spent on each task this week, then total by week, cycle, and project.
Name | Task3 | [9 empty] | Total Hours
2/10/11 - 2/16/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle 1 | Project
David Mason | 5 | 3 | 2 | [6 empty] | 1 | 11 | 11 | 11
Ed Budimier |  | 2 | 3 |  |  | 3 |  |  |  | 2 | 10 | 10 | 10
Shaquana Peterson |  | 2 |  |  | 2 | 4 |  |  |  | 2 | 10 | 10 | 10
Jens Johnson |  | 2 | 3 | 2 |  | 2 |  |  |  | 1 | 10 | 10 | 10
Adam Gould |  | 2 | 3 |  |  | 3 |  |  |  | 2 | 10 | 10 | 10
[10 empty] | Total | 51 | 51 | 51
2/17/11 - 2/23/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle 1 | Project
David Mason | 1.5 | [5 empty] | 1 | 1 | 1 | 2 | 6.5 | 17.5 | 17.5
Ed Budimier |  | 1 |  |  |  |  | 1 | 2 |  | 3 | 7 | 17 | 17
Shaquana Peterson | [5 empty] | 3 |  | 1 |  | 4 | 8 | 18 | 18
Jens Johnson |  |  |  | 1 |  |  | 3 |  | 1 | 2 | 7 | 17 | 17
Adam Gould | 1 |  |  | 1 |  |  | 2 |  | 2 |  | 6 | 16 | 16
[10 empty] | Total | 34.5 | 85.5 | 85.5
2/24/11 - 3/2/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle 1 | Project
David Mason | 2.5 | 1 |  |  |  |  | 1.5 |  | 3 | 3 | 11 | 28.5 | 28.5
Ed Budimier |  | 3 |  |  |  |  | 2 | 1 | 2 | 3 | 11 | 28 | 28
Shaquana Peterson | [5 empty] | 4 |  |  |  | 3 | 7 | 25 | 25
Jens Johnson |  | 1 |  | 2 |  |  |  |  | 1 | 3 | 7 | 24 | 24
Adam Gould |  | 1 |  |  | 3 | 2 | 1 | 2 | 1 | 3 | 13 | 29 | 29
[10 empty] | Total | 49 | 134.5 | 134.5
3/3/11 - 3/9/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle 1 | Project
David Mason | 4 | 2 | 1 |  |  | 1 |  |  | 1 | 2 | 11 | 39.5 | 39.5
Ed Budimier |  | 2 | 2 |  |  |  | 2 |  | 1 |  | 7 | 35 | 35
Shaquana Peterson |  | 2 |  |  | 1 | 2 |  |  |  | 2 | 7 | 32 | 32
Jens Johnson |  | 2 | 3 | 1 |  |  | 3 |  | 4 |  | 13 | 37 | 37
Adam Gould | [10 empty] | 0 | 29 | 29
[10 empty] | Total | 38 | 172.5 | 172.5
3/10/11 - 3/23/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle 2 | Project
David Mason | 2 | [6 empty] | 1 | 1 |  | 4 | 4 | 43.5
Ed Budimier | [5 empty] | 1 | 2 | 1 |  |  | 4 | 4 | 39
Shaquana Peterson | [10 empty] | 0 | 0 | 32
Jens Johnson |  |  |  | 1 |  |  |  |  | 1 |  | 2 | 2 | 39
Adam Gould | [10 empty] | 0 | 0 | 29
[10 empty] | Total | 10 | 10 | 182.5
Accomplishments since last status report:
1) Developed motor control circuitry and code. 2) Received all replacement parts.
Accomplishments must have some deliverable form (e.g., it cannot be stated that “serial interface programming was learned”; rather, data demonstrating those concepts learned must be presented (e.g. a program that successfully sends a character to serial port is demonstrated).
Obstacles encountered since last status report and actions to deal with same:
1) Could not get consistent readings from transmitter. Changed to direct motor control.
Risks facing the project and actions to deal with same:
1) Will we be able to use wireless communications? Program Xbee wireless communication system 2) Can't detect transmission signal. Use motor controllers instead.
Team members should review formal risk management concepts and incorporate those here.
Objectives for the next week:
1) Send a wireless sensor reading to another microcontroller 2) Integrate sensor readings into motor control program 3) Solder permanent circuit. 4) Balance the helicopter about main shaft.
Ideally, this week’s objectives will be next week’s accomplishments. Like accomplishments, these must be concrete and subject to physical demonstration.
Notes:

## David
Date | 2011-02-23
Hours per task
Cycle 1 | Hours per week | Team Management | 13
Week 1 | 11 | Reporting | 6
Week 2 | 6.5 | Editing | 3
Week 3 | 11 | Website Management
Week 4 | 11 | Budgeting
|  | Purchasing/Market Research | 1
|  | Programming | 2.5
|  | Circuit Design | 1
|  | Prototype Testing and Troubleshooting | 5
|  | Meeting | 8
|  | Total Hours | 39.5

## Edward
Date | 2011-02-23
Hours per task
Cycle 1 | Hours per week | Team Management
Week 1 | 10 | Reporting | 8
Week 2 | 7 | Editing | 5
Week 3 | 11 | Website Management
Week 4 | 7 | Budgeting
|  | Purchasing/Market Research | 3
|  | Programming | 5
|  | Circuit Design | 3
|  | Prototype Testing and Troubleshooting | 3
|  | Meeting | 8
|  | Total Hours | 35

## Shaquana
Date | 2011-02-23
Hours per task
Cycle 1 | Hours per week | Team Management
Week 1 | 10 | Reporting | 4
Week 2 | 8 | Editing
Week 3 | 7 | Website Management
Week 4 | 7 | Budgeting | 3
|  | Purchasing/Market Research | 13
Programming
|  | Circuit Design | 1
Prototype Testing and Troubleshooting
|  | Meeting | 11
|  | Total Hours | 32

## Jens
Date | 2011-02-23
Hours per task
Cycle 1 | Hours per week | Team Management
Week 1 | 10 | Reporting | 5
Week 2 | 7 | Editing | 6
Week 3 | 7 | Website Management | 6
Week 4 | 13 | Budgeting
|  | Purchasing/Market Research | 2
|  | Programming | 6
Circuit Design
|  | Prototype Testing and Troubleshooting | 6
|  | Meeting | 6
|  | Total Hours | 37

## Adam
Date | 2011-02-23
Hours per task
Cycle 1 | Hours per week | Team Management | 1
Week 1 | 10 | Reporting | 3
Week 2 | 6 | Editing | 3
Week 3 | 13 | Website Management | 1
Week 4 |  | Budgeting | 3
|  | Purchasing/Market Research | 5
|  | Programming | 3
|  | Circuit Design | 2
|  | Prototype Testing and Troubleshooting | 3
|  | Meeting | 5
|  | Total Hours | 29