## Status Report
ELEC 4000 Senior Design Status Report Excel Template Managed by: David Mason
Project Name: |  | AU Electro-Aviation
Team 1, Members: |  | Jens Johnson, Shaquana Peterson, Ed Budimier, David Mason, Adam Gould
Report Date: |  | 2011-03-30
Project Description: |  | Autonimous aviation with indoor helicopter.
Cycle (P, 1, or 2): |  | Cycle Two (2)
Cycle Intent: |  | Begin prototype by designing a front-end application and circuit design capable of replacing an electric, 26" indoor helicopter's existing control board.
TASKS
[8 empty] | Planned |  |  | Actual
Task # | Task Description (Add rows as needed) | [6 empty] | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status (%) Compl.. | Actual hours this cycle | Total Project Hours
1 | Team Management | [6 empty] | 2 | 7.5 | 30 |  | 5 | 19
2 | Reporting | [6 empty] | 2 | 2 | 8 |  | 0.5 | 26.5
3 | Editing | [6 empty] | 2 | 0.5 | 2 |  | 2 | 19
4 | Website Management | [6 empty] | 2 | 1 | 4 |  | 4 | 11
5 | Budgeting | [6 empty] | 2 | 1 | 4 |  | 0 | 6
6 | Purchasing/Market Research | [6 empty] | 2 | 1 | 4 |  | 8 | 33
7 | Programming | [6 empty] | 2 | 2 | 8 |  | 10.5 | 32
8 | Circuit Design | [6 empty] | 2 | 1 | 4 |  | 14 | 23
9 | Prototype Testing and Troubleshooting | [6 empty] | 2 | 1 | 4 |  | 26 | 54
10 | Meeting | [6 empty] | 2 | 3 | 12 |  | 22 | 64
To insert new row right click on this row number and click insert
1Planned Total should equal (# of team members) x (10 hrs. per week) x (Proposal weeks (3) + Cycle 1 weeks (4) + Cycle 2 weeks (5) = 12 weeks).
2Assumes 7.5 hours per week for 12 weeks. Should be mainly team leader(s).
TEAM MEMBER HOURS
Record # of hours each person spent on each task this week, then total by week, cycle, and project.
Name | Task3 | [9 empty] | Total Hours
2/10/11 - 2/16/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week 1 | Cycle 1 | Project
David Mason | Task3 1: 5; Task3 2: 3; Task3 3: 2; Task3 10: 1; Total Hours Week 1: 11; Total Hours Cycle 1: 11 | 11
Ed Budimier | Task3 2: 2; Task3 3: 3; Task3 6: 3; Task3 10: 2; Total Hours Week 1: 10; Total Hours Cycle 1: 10 | 10
Shaquana Peterson | Task3 2: 2; Task3 5: 2; Task3 6: 4; Task3 10: 2; Total Hours Week 1: 10; Total Hours Cycle 1: 10 | 10
Jens Johnson | Task3 2: 2; Task3 3: 3; Task3 4: 2; Task3 6: 2; Task3 10: 1; Total Hours Week 1: 10; Total Hours Cycle 1: 10 | 10
Adam Gould | Task3 2: 2; Task3 3: 3; Task3 6: 3; Task3 10: 2; Total Hours Week 1: 10; Total Hours Cycle 1: 10 | 10
Weekly Total | 5 | 11 | 11 | 2 | 2 | 12 | 0 | 0 | 0 | 8 | 51 | 51 | 51
Cycle Total | 5 | 11 | 11 | 2 | 2 | 12 | 0 | 0 | 0 | 8 | 51 | 51
2/17/11 - 2/23/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week 2 | Cycle 1 | Project
David Mason | 1: 1.5; 7: 1; 8: 1; 9: 1; 10: 2; Week 2: 6.5; Cycle 1: 17.5 | 17.5
Ed Budimier | 2: 1; 7: 1; 8: 2; 10: 3; Week 2: 7; Cycle 1: 17 | 17
Shaquana Peterson | 6: 3; 8: 1; 10: 4; Week 2: 8; Cycle 1: 18 | 18
Jens Johnson | 4: 1; 7: 3; 9: 1; 10: 2; Week 2: 7; Cycle 1: 17 | 17
Adam Gould | 1: 1; 4: 1; 7: 2; 9: 2; Week 2: 6; Cycle 1: 16 | 16
Weekly Total | 2.5 | 1 | 0 | 2 | 0 | 3 | 7 | 4 | 4 | 11 | 34.5 | 85.5 | 85.5
Cycle Total | 7.5 | 12 | 11 | 4 | 2 | 15 | 7 | 4 | 4 | 19 | 85.5 | 136.5
2/24/11 - 3/2/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week 3 | Cycle 1 | Project
David Mason | 1: 2.5; 2: 1; 7: 1.5; 9: 3; 10: 3; Week 3: 11; Cycle 1: 28.5 | 28.5
Ed Budimier | 2: 3; 7: 2; 8: 1; 9: 2; 10: 3; Week 3: 11; Cycle 1: 28 | 28
Shaquana Peterson | 6: 4; 10: 3; Week 3: 7; Cycle 1: 25 | 25
Jens Johnson | 2: 1; 4: 2; 9: 1; 10: 3; Week 3: 7; Cycle 1: 24 | 24
Adam Gould |  | 1 |  |  | 3 | 2 | 1 | 2 | 1 | 3 | 13 | 29 | 29
Weekly Total | 2.5 | 6 | 0 | 2 | 3 | 6 | 4.5 | 3 | 7 | 15 | 49 | 134.5 | 134.5
Cycle Total | 10 | 18 | 11 | 6 | 5 | 21 | 11.5 | 7 | 11 | 34 | 134.5 | 271
3/3/11 - 3/9/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week 4 | Cycle 1 | Project
David Mason | 4 | 2 | 1 |  |  | 1 |  |  | 1 | 2 | 11 | 39.5 | 39.5
Ed Budimier | 2: 2; 3: 2; 7: 2; 9: 1; Week 4: 7; Cycle 1: 35 | 35
Shaquana Peterson | 2: 2; 5: 1; 6: 2; 10: 2; Week 4: 7; Cycle 1: 32 | 32
Jens Johnson | 2: 2; 3: 3; 4: 1; 7: 3; 9: 4; Week 4: 13; Cycle 1: 37 | 37
Adam Gould | 6: 1; 7: 5; 8: 2; 9: 11; 10: 4; Week 4: 23; Cycle 1: 52 | 52
Weekly Total | 4 | 8 | 6 | 1 | 1 | 4 | 10 | 2 | 17 | 8 | 61 | 195.5 | 195.5
Cycle Total | 14 | 26 | 17 | 7 | 6 | 25 | 21.5 | 9 | 28 | 42 | 195.5 | 466.5
3/10/11 - 3/23/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week 1 | Cycle 2 | Project
David Mason | 1: 2; 2: 0.5; 8: 1; 9: 1; 10: 3; Week 1: 7.5; Cycle 2: 7.5 | 47
Ed Budimier | 6: 1; 7: 2; 8: 1; 10: 3; Week 1: 7; Cycle 2: 7 | 42
Shaquana Peterson | 6: 2; 9: 4; 10: 3; Week 1: 9; Cycle 2: 9 | 41
Jens Johnson | 4: 2; 6: 1; 8: 1; 9: 1; 10: 2; Week 1: 7; Cycle 2: 7 | 44
Adam Gould | 6: 2; 7: 4; 8: 4; 9: 11; 10: 4; Week 1: 25; Cycle 2: 25 | 77
Weekly Total | 2 | 0.5 | 0 | 2 | 0 | 6 | 6 | 7 | 17 | 15 | 55.5 | 55.5 | 251
Cycle Total | 2 | 0.5 | 0 | 2 | 0 | 6 | 6 | 7 | 17 | 15 | 55.5 | 55.5
3/24/11 - 3/30/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week 2 | Cycle 2 | Project
David Mason | 3 |  |  |  |  | 1 | 0.5 | 3 | 6 | 1 | 14.5 | 22 | 61.5
Ed Budimier | 3: 2; 7: 4; 8: 3; 9: 2; 10: 2; Week 2: 13; Cycle 2: 20 | 55
Shaquana Peterson | 6: 1; 8: 1; 9: 1; 10: 2; Week 2: 5; Cycle 2: 14 | 46
Jens Johnson | 4: 2; 10: 2; Week 2: 4; Cycle 2: 11 | 48
Adam Gould | Week 2: 0; Cycle 2: 25 | 77
Weekly Total | 3 | 0 | 2 | 2 | 0 | 2 | 4.5 | 7 | 9 | 7 | 36.5 | 92 | 287.5
Cycle Total | 5 | 0.5 | 2 | 4 | 0 | 8 | 10.5 | 14 | 26 | 22 | 92 | 147.5
3/31/11 - 4/6/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week 3 | Cycle 2 | Project
David Mason | Week 3: 0; Cycle 2: 22 | 61.5
Ed Budimier | Week 3: 0; Cycle 2: 20 | 55
Shaquana Peterson | Week 3: 0; Cycle 2: 14 | 46
Jens Johnson | Week 3: 0; Cycle 2: 11 | 48
Adam Gould | Week 3: 0; Cycle 2: 25 | 77
Weekly Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 287.5
Cycle Total | 5 | 0.5 | 2 | 4 | 0 | 8 | 10.5 | 14 | 26 | 22 | 92 | 239.5
4/7/11 - 4/13/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week 4 | Cycle 2 | Project
David Mason | Week 4: 0; Cycle 2: 22 | 61.5
Ed Budimier | Week 4: 0; Cycle 2: 20 | 55
Shaquana Peterson | Week 4: 0; Cycle 2: 14 | 46
Jens Johnson | Week 4: 0; Cycle 2: 11 | 48
Adam Gould | Week 4: 0; Cycle 2: 25 | 77
Weekly Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 287.5
Cycle Total | 5 | 0.5 | 2 | 4 | 0 | 8 | 10.5 | 14 | 26 | 22 | 92 | 331.5
4/14/11 - 4/20/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week 5 | Cycle 2 | Project
David Mason | Week 5: 0; Cycle 2: 22 | 61.5
Ed Budimier | Week 5: 0; Cycle 2: 20 | 55
Shaquana Peterson | Week 5: 0; Cycle 2: 14 | 46
Jens Johnson | Week 5: 0; Cycle 2: 11 | 48
Adam Gould | Week 5: 0; Cycle 2: 25 | 77
Weekly Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 287.5
Cycle Total | 5 | 0.5 | 2 | 4 | 0 | 8 | 10.5 | 14 | 26 | 22 | 92 | 423.5
Accomplishments since last status report:
1) Built 5V power supply for sensors. 2) Confirmed that the helicopter still flies with new blades and control board. 3) Confirmed PING))) u-sonic sensors work when parallel to one another. 4) Collected motor charactreistics data.
Accomplishments must have some deliverable form (e.g., it cannot be stated that “serial interface programming was learned”; rather, data demonstrating those concepts learned must be presented (e.g. a program that successfully sends a character to serial port is demonstrated).
Obstacles encountered since last status report and actions to deal with same:
1) Problems designing the motor control circuit; High amperage is frying BJTs. Looking into MOSFETs, H-Bridges, ICs, and Shields.
Risks facing the project and actions to deal with same:
1) Have not yet compiled main program. Put together parameterless program and insert constants at a later date. 2) Can't detect transmission signal. Use motor controllers instead.
Team members should review formal risk management concepts and incorporate those here.
Objectives for the next week:
1) Develop delay cycle for PING readings to avoid interference and power dissipation problems. 2) Design motor control circuit by Friday or else buy motor control IC. 3) Solder power supply circuit to permanent board. 4) Compile Main() program.
Ideally, this week’s objectives will be next week’s accomplishments. Like accomplishments, these must be concrete and subject to physical demonstration.
Notes:

## David
Date | 2011-03-30 |  | Hours per task
|  |  | Cycle 1 | Cycle 2 | Project
Cycle 1 | Hours per week | Team Management | 13 | 5 | 18
Week 1 | 11 | Reporting | 6 | 0.5 | 6.5
Week 2 | 6.5 | Editing | 3 |  | 3
Week 3 | 11 | Website Management
Week 4 | 11 | Budgeting
|  | Purchasing/Market Research | 1 | 1 | 2
Cycle 2 | Hours per week | Programming | 2.5 | 0.5 | 3
Week 1 | 7.5 | Circuit Design | 1 | 4 | 5
Week 2 | 14.5 | Prototype Testing and Troubleshooting | 5 | 7 | 12
Week 3 |  | Meeting | 8 | 4 | 12
Week 4
Week 5 |  | Total | 39.5 | 22 | 61.5

## Edward
Date | 2011-03-30 |  | Hours per task
|  |  | Cycle 1 | Cycle 2 | Project
Cycle 1 | Hours per week | Team Management
Week 1 | 10 | Reporting | 8 |  | 8
Week 2 | 7 | Editing | 5 | 2 | 7
Week 3 | 11 | Website Management
Week 4 | 7 | Budgeting
|  | Purchasing/Market Research | 3 | 1 | 4
Cycle 2 | Hours per week | Programming | 5 | 6 | 11
Week 1 | 7 | Circuit Design | 3 | 4 | 7
Week 2 | 13 | Prototype Testing and Troubleshooting | 3 | 2 | 5
Week 3 |  | Meeting | 8 | 5 | 13
Week 4
Week 5 |  | Total | 35 | 20 | 55

## Shaquana
Date | 2011-03-30 |  | Hours per task
|  |  | Cycle 1 | Cycle 2 | Project
Cycle 1 | Hours per week | Team Management
Week 1 | 10 | Reporting | 4 |  | 4
Week 2 | 8 | Editing
Week 3 | 7 | Website Management
Week 4 | 7 | Budgeting | 3 |  | 3
|  | Purchasing/Market Research | 13 | 3 | 16
Cycle 2 | Hours per week | Programming
Week 1 | 9 | Circuit Design | 1 | 1 | 2
Week 2 | 5 | Prototype Testing and Troubleshooting |  | 5 | 5
Week 3 |  | Meeting | 11 | 5 | 16
Week 4
Week 5 |  | Total | 32 | 14 | 46

## Jens
Date | 2011-03-30 |  | Hours per task
|  |  | Cycle 1 | Cycle 2 | Project
Cycle 1 | Hours per week | Team Management
Week 1 | 10 | Reporting | 5 |  | 5
Week 2 | 7 | Editing | 6 |  | 6
Week 3 | 7 | Website Management | 6 | 4 | 10
Week 4 | 13 | Budgeting
|  | Purchasing/Market Research | 2 | 1 | 3
Cycle 2 | Hours per week | Programming | 6 |  | 6
Week 1 | 7 | Circuit Design |  | 1 | 1
Week 2 | 4 | Prototype Testing and Troubleshooting | 6 | 1 | 7
Week 3 |  | Meeting | 6 | 4 | 10
Week 4
Week 5 |  | Total | 37 | 11 | 48

## Adam
Date | 2011-03-30 |  | Hours per task
|  |  | Cycle 1 | Cycle 2 | Project
Cycle 1 | Hours per week | Team Management | 1 |  | 1
Week 1 | 10 | Reporting | 3 |  | 3
Week 2 | 6 | Editing | 3 |  | 3
Week 3 | 13 | Website Management | 1 |  | 1
Week 4 | 23 | Budgeting | 3 |  | 3
|  | Purchasing/Market Research | 6 | 2 | 8
Cycle 2 | Hours per week | Programming | 8 | 4 | 12
Week 1 | 25 | Circuit Design | 4 | 4 | 8
Week 2 |  | Prototype Testing and Troubleshooting | 14 | 11 | 25
Week 3 |  | Meeting | 9 | 4 | 13
Week 4
Week 5 |  | Total | 52 | 25 | 77