## Sheet1
ELEC 4000 Senior Design Status Report Excel Template Created by: David Mason
Project Name: |  | AU Electro-Aviation
Team 1, Members: |  | Jens Johnson, Shaquana Peterson, Ed Budimier, David Mason, Adam Gould
Report Date: |  | 2011-02-16
Project Description: |  | Autonimous aviation with indoor helicopter.
Cycle (P, 1, or 2): |  | Cycle One (1)
Cycle Intent: |  | Begin prototype by designing a front-end application and circuit design capable of being interfaced to an electric, 26" indoor helicopter's existing control board.
TASKS
[8 empty] | Planned |  |  | Actual
Task # | Task Description (Add rows as needed) | [6 empty] | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status (%) Compl.. | Actual hours this cycle | Total Hours
1 | Team Management | [6 empty] | 1 | 7.5 | 30
2 | Reporting | [6 empty] | 1 | 2 | 8
3 | Editing | [6 empty] | 1 | 0.5 | 2
4 | Website Management | [6 empty] | 1 | 1 | 4
5 | Budgeting | [6 empty] | 1 | 1 | 4
6 | Purchasing/Market Research | [6 empty] | 1 | 1 | 4
7 | Programming | [6 empty] | 1 | 2 | 8
8 | Circuit Design | [6 empty] | 1 | 1 | 4
9 | Prototype Testing and Troubleshooting | [6 empty] | 1 | 1 | 4
10 | Meeting | [6 empty] | 1 | 3 | 12
To insert new row right click on this row number and click insert
1Planned Total should equal (# of team members) x (10 hrs. per week) x (Proposal weeks (3) + Cycle 1 weeks (4) + Cycle 2 weeks (5) = 12 weeks).
2Assumes 7.5 hours per week for 12 weeks. Should be mainly team leader(s).
TEAM MEMBER HOURS
Record # of hours each person spent on each task this week, then total by week, cycle, and project.
Name | Task3 | [9 empty] | Total Hours
2/10/11 - 2/16/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle | Project
David Mason | 5 | 3 | 2 | [6 empty] | 1 | 11 | 11 | 11
Ed Budimier |  | 2 | 3 |  |  | 3 |  |  |  | 2 | 10 | 10 | 10
Shaquana Peterson |  | 2 |  |  | 2 | 4 |  |  |  | 2 | 10 | 10 | 10
Jens Johnson |  | 2 | 3 | 2 |  | 2 |  |  |  | 1 | 10 | 10 | 10
Adam Gould |  | 2 | 4 |  |  | 3 |  |  |  | 2 | 11 | 11 | 11
[10 empty] | Total | 52 | 52 | 52
2/17/11 - 2/23/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle | Project
David Mason | [10 empty] | 0 | 11 | 11
Ed Budimier | [10 empty] | 0 | 10 | 10
Shaquana Peterson | [10 empty] | 0 | 10 | 10
Jens Johnson | [10 empty] | 0 | 10 | 10
Adam Gould | [10 empty] | 0 | 11 | 11
[10 empty] | Total | 0 | 52 | 52
2/24/11 - 3/2/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle | Project
David Mason | [10 empty] | 0 | 11 | 11
Ed Budimier | [10 empty] | 0 | 10 | 10
Shaquana Peterson | [10 empty] | 0 | 10 | 10
Jens Johnson | [10 empty] | 0 | 10 | 10
Adam Gould | [10 empty] | 0 | 11 | 11
[10 empty] | Total | 0 | 52 | 52
3/3/11 - 3/9/11 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Week | Cycle | Project
David Mason | [10 empty] | 0 | 11 | 11
Ed Budimier | [10 empty] | 0 | 10 | 10
Shaquana Peterson | [10 empty] | 0 | 10 | 10
Jens Johnson | [10 empty] | 0 | 10 | 10
Adam Gould | [10 empty] | 0 | 11 | 11
[10 empty] | Total | 0 | 52 | 52
Accomplishments since last status report:
1) Purchased Double Horse 9053 Volitation 26" helicopter and replacement rotor blades. 2) Purchased Arduino Controller and IR range sensor and power supply.
Accomplishments must have some deliverable form (e.g., it cannot be stated that “serial interface programming was learned”; rather, data demonstrating those concepts learned must be presented (e.g. a program that successfully sends a character to serial port is demonstrated).
Obstacles encountered since last status report and actions to deal with same:
1) This week marked the beginning of the Cycle 1 phase of the project. Our team met Friday February 11th at 11:00 am to discuss our first steps.
Risks facing the project and actions to deal with same:
1) The helicopter's payload handling is a mystery at this point, so we don’t know which components to purchase. To deal with this we are going to attatch sandbags to the helicopter to determine its maximum payload.
Team members should review formal risk management concepts and incorporate those here.
Objectives for the next week:
1) Determine helicopter's maximum payload. 2) Find a way to open the helicopter's frame work and get to it's existing control board. 3) Start Prototying the controller and sensors
Ideally, this week’s objectives will be next week’s accomplishments. Like accomplishments, these must be concrete and subject to physical demonstration.
Notes:

## David
Cycle 1 | 2011-02-16
Week 1 | 0
Week 2
Week 3
Week 4
Week 5